## Лист1
date | work done | Ttime
25 december | start to share basic tools and layouts on react framework | 8h
26 december | finish to implement basic layouts components on react | 9h
27 december | start to implement frames component, fix errors with pen tool | 5h
28 december | start to implement stroke tool, frames add/delete logic | 6h
30 december | finish to add stroke component withput drawing line effect | 18h
03 january | finish to implement drag and drop, fix erros with add/delete/clone frames | 10h
04 january | start working with tests | 5h
05 january | implement google sign in authentification, implement save gif tool | 6h
06 january | implement buckets tool | 2h
07 january | fix bucket tool - to bucket the current area | 11h
8 january | working with test, fix some bugs and refactor the code | 13h
| Total | 103h